## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to view personalized product recommendations on the homepage | MUST HAVE | None | Goku Nathan | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want the system to collect and preprocess my browsing and purchase history for recommendations | MUST HAVE | US-01 | Goku Nathan | 3- Completed
Sprint 2 | Sprint 2 | US-03 | As a user, I want content-based product recommendations using TF-IDF similarity based on product tags | MUST HAVE | US-02 | Goku Nathan | 3- Completed
Sprint 2 | Sprint 2 | US-04 | As a user, I want collaborative filtering recommendations based on the behaviour of similar users | MUST HAVE | US-02 | Goku Nathan | 3- Completed
Sprint 2 | Sprint 2 | US-05 | As a new user, I want to see popular product recommendations when I have no purchase history (cold-start fallback) | SHOULD HAVE | US-03 | Goku Nathan | 3- Completed
Sprint 3 | Sprint 3 | US-06 | As a user, I want recommendation accuracy validated using precision, recall, and F1-score metrics | MUST HAVE | US-03, US-04 | Goku Nathan | 3- Completed
Sprint 3 | Sprint 3 | US-07 | As a user, I want fast recommendations with API response time under 2 seconds | SHOULD HAVE | US-06 | Goku Nathan | 3- Completed
Sprint 4 | Sprint 4 | US-08 | As a user, I want the recommendation engine integrated into the product detail page of the ShopSmart frontend | MUST HAVE | US-03 | Goku Nathan | 3- Completed
Sprint 4 | Sprint 4 | US-09 | As a user, I want to interact with an AI chat assistant (Gemini) for shopping help inside the platform | COULD HAVE | None | Goku Nathan | 3- Completed
Sprint 4 | Sprint 4 | US-10 | As an admin, I want the full system deployed on a live environment (Railway/Vercel) and accessible via browser | MUST HAVE | US-08 | Goku Nathan | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG (Weeks 1–2: Data Preparation)
US-01 | T-01 | Collect raw product and user interaction dataset (cleaned_output.csv) | 12-Feb-26 | 13-Feb-26 | Team | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-02 | Explore dataset: review columns, types, missing values | 13-Feb-26 | 16-Feb-26 | Team | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Clean dataset: handle missing values, remove duplicates, normalise fields | 16-Feb-26 | 18-Feb-26 | Team | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Build user-item interaction matrix from ratings data | 18-Feb-26 | 18-Feb-26 | Team | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG (Weeks 3–4: Model Building)
US-03 | T-05 | Implement TF-IDF vectorizer on product Tags column | 19-Feb-26 | 20-Feb-26 | Team | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-06 | Compute cosine similarity matrix for content-based filtering | 20-Feb-26 | 23-Feb-26 | Team | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-07 | Build collaborative filtering model using user-user cosine similarity | 23-Feb-26 | 25-Feb-26 | Team | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-08 | Implement cold-start fallback: return top-rated products for new users | 25-Feb-26 | 25-Feb-26 | Team | Design | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG (Weeks 5–6: Evaluation & Refinement)
US-06 | T-09 | Calculate precision, recall, and F1-score on recommendation results | 26-Feb-26 | 02-Mar-26 | Team | Unit Test | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-10 | Precompute similarity matrix at startup to reduce API response time | 02-Mar-26 | 03-Mar-26 | Team | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-11 | Tune TF-IDF parameters (max_features, stop_words) for accuracy improvement | 03-Mar-26 | 04-Mar-26 | Team | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-12 | Implement duplicate filtering in recommendation output | 04-Mar-26 | 04-Mar-26 | Team | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG (Weeks 7–8: Deployment & Integration)
US-08 | T-13 | Integrate recommendation API endpoint with React ProductPage.jsx | 19-Mar-26 | 23-Mar-26 | Team | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-14 | Integrate Gemini AI chat assistant into frontend | 23-Mar-26 | 25-Mar-26 | Team | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-15 | Deploy FastAPI backend to Railway; configure environment variables | 25-Mar-26 | 25-Mar-26 | Team | Build | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-16 | Deploy React frontend to Vercel; verify end-to-end functionality | 25-Mar-26 | 26-Mar-26 | Team | Build | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-17 | Conduct final functional and performance tests on live environment | 26-Mar-26 | 30-Mar-26 | Team | Unit Test | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Collected and loaded cleaned_output.csv product dataset; reviewed schema and column types
Sprint 1 | Day 2 | Missing values in user purchase history and inconsistent rating formats | Handled missing values with pandas fillna; standardised Rating and Review Count to numeric
Sprint 1 | Day 3 | Difficulty deciding between collaborative and content-based filtering | Reviewed both approaches; decided to implement both TF-IDF (content) and user-user cosine similarity (collaborative)
Sprint 1 | Day 4 | Cold-start problem: no recommendation available for new users | Designed popularity-based fallback to return top-rated products for users with no history
Sprint 1 | Day 5 | User-item matrix very sparse due to limited rating data | Applied mean-fill on pivot table; proceeded with cosine similarity on available ratings
Sprint 2 | Day 1 | None | Implemented TF-IDF vectorizer on product Tags; computed cosine similarity matrix
Sprint 2 | Day 2 | Similarity matrix computation slow for large dataset | Restricted max_features to 500 and precomputed at startup to reduce per-request latency
Sprint 2 | Day 3 | Collaborative model returning irrelevant results for edge-case users | Filtered invalid User IDs (values < 0); verified pivot table correctness
Sprint 2 | Day 4 | None | Completed collaborative filtering model; integrated both models into FastAPI routes
Sprint 2 | Day 5 | Duplicate products appearing in recommendation output | Added deduplication step before returning recommendation list from API
Sprint 3 | Day 1 | None | Computed precision, recall, and F1-score on sample recommendation outputs
Sprint 3 | Day 2 | Precision below 60% for niche categories with sparse tags | Expanded product tag fields; retrained TF-IDF; improved precision to ~72%
Sprint 3 | Day 3 | API response time exceeding 5 seconds on recommendations endpoint | Precomputed similarity matrix at app startup; response time reduced to under 2 seconds
Sprint 3 | Day 4 | None | Fine-tuned TF-IDF parameters; tested different recommendation scenarios; results validated
Sprint 3 | Day 5 | None | Finalised evaluation report; all metrics met target thresholds; model ready for deployment
Sprint 4 | Day 1 | None | Integrated recommendation API with React ProductPage.jsx; tested rendering on frontend
Sprint 4 | Day 2 | API response format mismatch causing frontend rendering errors | Updated API response schema; fixed ProductPage.jsx component to match new format
Sprint 4 | Day 3 | Gemini API key management and secure env variable setup | Configured GEMINI_API_KEY as environment variable; verified AI chat assistant functionality
Sprint 4 | Day 4 | Deployment issues on Railway due to missing requirements | Added all dependencies to requirements.txt; resolved Railway deployment build errors
Sprint 4 | Day 5 | None | Full system deployed on Railway (backend) and Vercel (frontend); end-to-end tests passed; project completed

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | 1 | 12-Feb-26 | 18-Feb-26 | Team | Begin data profiling and exploratory analysis before any modelling decisions | Jumping into model implementation without sufficient data understanding | Structured sprint planning with clear objectives per milestone | Adopted a data-first approach; EDA guided algorithm selection
2 | 2 | 19-Feb-26 | 25-Feb-26 | Team | Modularise ML code early to separate data, model, and API concerns | Writing monolithic functions that mix preprocessing with model logic | Peer review of algorithm design before implementation | Refactored main.py to clearly separate model loading, preprocessing, and route logic
3 | 3 | 26-Feb-26 | 04-Mar-26 | Team | Define evaluation metrics before starting the refinement phase | Optimising for speed before achieving acceptable accuracy | Regular metric tracking after each tuning iteration | Tracked precision, recall, and F1 after each parameter change; documented improvements
4 | 4 | 19-Mar-26 | 30-Mar-26 | Team | Set up CI/CD deployment pipeline from the beginning of the project | Manual deployment steps without version-controlled configuration | Testing both backend and frontend integration at each sprint end | Deployed to Railway and Vercel with environment variable management; final integration tests passed