## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Submitted Date | Status(Open/Closed) | Remarks
1 | Gokul Nathan | 2026-02-12 | Missing values in user purchase history causing errors in user-item matrix construction | Sprint 1 – Data Preparation | Self | Logical | Cleaned dataset using pandas: filled missing values and removed inconsistent rows | 2026-02-12 | Closed | User-item matrix built successfully
2 | Gokul Nathan | 2026-02-22 | Cold-start problem: new users received no recommendations | Sprint 2 – Model Building | Self | Logical | Implemented fallback logic using popularity-based recommendations for new users | 2026-02-22 | Closed | New users now receive top-rated product suggestions
3 | Gokul Nathan | 2026-02-28 | Duplicate products appearing in TF-IDF recommendation output | Sprint 3 – Evaluation & Refinement | Self | Maintainability | Added deduplication filter on recommendation results before API response | 2026-02-28 | Closed | All recommendation lists contain unique products
4 | Gokul Nathan | 2026-03-10 | Slow API response time (>5 sec) on /recommendations endpoint | Sprint 3 – Evaluation & Refinement | Self | Standards | Precomputed TF-IDF similarity matrix at startup; added response caching | 2026-03-10 | Closed | Response time reduced to <2 seconds
5 | Gokul Nathan | 2026-03-20 | Frontend React component fails to render recommendation cards on ProductPage | Sprint 4 – Deployment & Integration | Self | User Interface | Fixed API response format mismatch; updated ProductPage.jsx rendering logic | 2026-03-20 | Closed | Recommendations display correctly on all product pages
6 | Gokul Nathan | 2026-03-30 | JWT token not invalidated on logout; users can re-use expired tokens | Sprint 4 – Deployment & Integration | Self | Standards | Added token blacklist in-memory store and validated on each protected route | 2026-03-30 | Closed | Logout correctly blocks reuse of old tokens

## Sheet2
Logical
User Interface
Maintainability
Standards
Others